## Defects
Defect ID | Date | Instance | Module | Title | Description | Test Data / Required Info | Status | Screenshot / STR | Priority | Severity | Type | Retested Result | Developer Assigned | Resolved Date | Developer Comment | QA Comment | Changes Applied
DEF-001 | 28-Jul-2026 | QA | Login | User ID field does not validate email format client-side | Entering an invalid User ID format (e.g. "not-an-email") is not rejected client-side; the app calls the auth API regardless and surfaces a generic "credentials incorrect" toast instead of a field-level email-format validation error. | Chrome (Desktop); URL: /login; Input: "not-an-email" / any password | New | Automated: TC-LOGIN-008 in tests/LP_TS001/field-validation.spec.ts | Medium | Minor | Validation | Not Retested |  |  |  | Confirmed via automated TC-LOGIN-008, reproduced consistently across multiple runs.
BUG-006 | 28-Jul-2026 | QA | Homepage - Branding | SAHAYOG and Government logos are not rendered anywhere on the Homepage | Only the Netwin logo (Powered By netwin v1.05) renders in the sidebar; no SAHAYOG or Government branding image exists in the DOM, contradicting the original Homepage branding requirements. | User: nayan.aher@netwinindia.in; Chrome (Desktop); URL: /HOME after login | New | screenshots/homepage/BUG-006_Missing-SAHAYOG-Government-Logo.png | High | Major | UI | Not Retested |  |  |  | Confirmed via automated TC-HOME-008 and DOM inspection. Not covered by current US_HOME_001 acceptance criteria, so not re-verified in the latest cycle, but unresolved.
BUG-007 | 28-Jul-2026 | QA | Homepage - Footer | Footer renders with no copyright text | footer.am-footer exists but its .am-foot-copyright child is empty; the footer also fails a basic visibility check. | User: nayan.aher@netwinindia.in; Chrome (Desktop); URL: /HOME after login | New | screenshots/homepage/BUG-007_Empty-Footer-Copyright-Confirmed.png (corroborates pre-existing BUG-004_empty-footer-highlighted.png) | Medium | Minor | UI | Not Retested |  |  |  | Confirmed via automated TC-HOME-011. Not covered by current US_HOME_001 acceptance criteria, so not re-verified in the latest cycle, but unresolved.
DEF-002 | 28-Jul-2026 | QA | Forgot User ID | Reloading /forgetUser redirects to Login instead of preserving the recovery flow | A hard reload of /forgetUser drops the client-side route entirely and lands back on /login, losing the user's place in the recovery flow. Unlike /login (the SPA fallback route, which trivially survives a reload). | Chrome (Desktop); URL: /forgetUser (any step); Action: browser reload | New | Automated: TC-FUI-017b in tests/FUI_TS001/step1-email-recovery.spec.ts | Low | Minor | Functional | Not Retested |  |  |  | Confirmed via automated TC-FUI-017b, reproduces consistently.
DEF-003 | 28-Jul-2026 | QA | Forgot User ID | Send Reference ID button is not disabled while its request is in flight | A rapid double-click on Send Reference ID fires two identical ref/request calls instead of the second click being blocked, wasting a rate-limited Reference ID request per accidental double-click. | Chrome (Desktop); URL: /forgetUser; Action: rapid double-click Send Reference ID | New | Automated: TC-FUI-016 in tests/FUI_TS001/step1-email-recovery.spec.ts | Medium | Major | Functional | Not Retested |  |  |  | Confirmed via automated TC-FUI-016, independently re-verified across multiple runs (including after correcting an unrelated test-data mobile-number mix-up) to rule out a false positive.