## Defects
Defect ID | Date | Instance | Module | Title | Description | Test Data / Required Info | Status | Screenshot / STR | Priority | Severity | Type | Retested Result | Developer Assigned | Resolved Date | Developer Comment | QA Comment | Changes Applied
BUG-FP-001 | 29-Jul-2026 | QA | Forgot Password | Whitespace-only User ID does not disable Send Reference ID | Unlike a genuinely blank field, entering only spaces into User ID does not keep the Send Reference ID button disabled. The server does correctly reject the resulting request ("User not found") rather than succeeding, but the client-side gate that should stop the request from firing at all is missing. | Chrome (Desktop); URL: /forgetPassword; Input: " " (whitespace only) | New | Automated: TC-FP-005 in tests/FP_TS001/forgot-password.spec.ts; corroborates pre-existing screenshots/forgot-password/BUG-FP-001_whitespace-userid-enables-button.png | Medium | Minor | Validation | Not Retested |  |  |  | Confirmed via automated TC-FP-005, corroborates an independent pre-existing exploratory finding.
BUG-FP-002 | 29-Jul-2026 | QA | Forgot Password | Intermittent Reference ID delivery delay/failure | 2 of 4 real Send Reference ID attempts for Forgot Password did not deliver (SMS or email) within a 5-minute wait, despite the app reporting success each time. The sibling Forgot User ID flow delivered reliably (2/2) to the same registered number in the same session, suggesting the issue is specific to Forgot Password's delivery path (or intermittently affects it) rather than the account/number itself. | User: nayan.aher@netwinindia.in; Registered number: 9511996248; Chrome (Desktop); URL: /forgetPassword | New | Observed across 4 live attempts of TC-FP-020 in tests/FP_TS001/forgot-password.spec.ts on 28-29 Jul 2026 | Low | Minor | Functional | Not Retested |  |  |  | Not a hard functional defect - flow works correctly whenever delivery succeeds. Logged for delivery-reliability investigation.