## Defects
Defect ID | Date | Instance | Module | Title | Description | Test Data / Required Info | Status | Screenshot / STR | Priority | Severity | Type | Retested Result | Developer Assigned | Resolved Date | Developer Comment | QA Comment | Changes Applied
BUG-SILVER-001 | 05-Aug-2026 | QA | Silver Savings Account Journey | Document uploads accept any correctly-typed file with no content validation | Every document-upload point in the journey (PAN, Driving Licence, Voter ID, Address Proof, Applicant Signature) accepts any file that passes extension filtering (png/jpg/pdf) regardless of what it actually depicts. An unrelated app screenshot was accepted as a valid PAN card, and a fake test-camera capture was accepted as a valid handwritten signature. File-extension filtering itself works correctly. | Chrome (Desktop); URL: /applndetails; test files: unrelated .png screenshot, Chromium fake video device capture | New | Confirmed live on applications SAH-1002-800 and SAH-1002-798, TC-SIL-034/103 in specs/SILVER_TS001-test-plan.md | Medium | Minor | Security | Not Retested |  |  |  | Confirmed via live execution across PAN, DL, Voter ID, and Applicant Signature upload points.
BUG-SILVER-002 | 05-Aug-2026 | QA | Silver Savings Account Journey | Address auto-fill never populates State/City/Pin Code | The "Same as Permanent address" checkbox and the "Use Existing Address" toggle only populate Address Line 1 (entire address dumped as one string) — State, City, and Pin Code are always left empty, despite showing "Address fetched successfully!". Confirmed on 3 separate address-collection screens (primary applicant Communication Address, joint applicant Permanent + Communication Address). | Chrome (Desktop); URL: /applndetails; Address Details step (multiple occurrences) | New | Confirmed live on application SAH-1002-798, TC-SIL-061 in specs/SILVER_TS001-test-plan.md | Medium | Minor | Functional | Not Retested |  |  |  | Systemic issue confirmed across 3 distinct address-collection screens in the same journey.
BUG-SILVER-003 | 05-Aug-2026 | QA | Silver Savings Account Journey | Spouse/Father's Name field silently truncates at 20 characters | The "Spouse / Father's Name" field on Basic Details accepts longer input in the UI but silently truncates the stored value at 20 characters with no warning. "Aishwarya Shubham Borse" (24 chars) was stored as "Aishwarya Shubham Bo" — confirmed via the field's live DOM value and reflected in the final Summary review. | Chrome (Desktop); URL: /applndetails; Basic Details step; Input: "Aishwarya Shubham Borse" | New | Confirmed live on application SAH-1002-798, TC-SIL-082 in specs/SILVER_TS001-test-plan.md | Medium | Minor | Validation | Not Retested |  |  |  | Confirmed via both live DOM inspection and the persisted final Summary page.
BUG-SILVER-004 | 05-Aug-2026 | QA | Silver Savings Account Journey | Security Code Liveliness does not verify applicant identity | Security Code Based Liveliness Verification — intended to confirm a live human matches the applicant's identity — returns "Successful" when a completely different person (not the actual applicant) holds up the security code in front of the camera. The check only verifies the photo contains the correct code text; it never checks the photographed person's face against the applicant's Aadhaar photo. Confirmed independently on two separate real applications (SAH-1002-800 and SAH-1002-798). | Real phone camera, real security code, different real person than the applicant; both applications SAH-1002-800 and SAH-1002-798 | New | Confirmed live twice, TC-SIL-053 in specs/SILVER_TS001-test-plan.md | Critical | Blocker | Security | Not Retested |  |  |  | HIGH PRIORITY: genuine KYC/compliance gap in a banking account-opening flow — recommend escalating beyond standard defect triage.
BUG-SILVER-005 | 07-Aug-2026 | UAT | Silver Savings Account — Basic Details (Employment Type / Funding Mode routing) | "Employment type is invalid for Minor" incorrectly blocks Basic Details submission for a confirmed adult Individual applicant when Employment Type = Agriculture/Farmer, Other, or Business (and inconsistently for Unemployed) | On application SAH-1002-775 — confirmed Customer Type "Individual" (checkmark verified on the Account Type tab) and a real, disabled, adult Date of Birth (1995-09-21, ~31 years old) — submitting Basic Details with Employment Type = Agriculture/Farmer, Other, or Business is consistently rejected with the inline error "Employment type is invalid for Minor.", regardless of Funding Mode (Cash or Cheque). Employment Type = Unemployed reproduced the same block in 3 of 4 real attempts; the 1 attempt that did not error still did not reach the correct destination. Cross-referenced against the project's routing configuration (aoscust_module_rules_setting.xlsx): RULE_24 should route "Farmer" to Self Employed Information, and Other/Business/Unemployed (matching no Employment-Type rule, and Customer Type is neither Joint nor Minor) should fall through to the Default rule and reach Applicant Photo. Neither destination is ever reached for these Employment Types. Suspected root causes: (1) the dropdown's literal value "Agriculture/Farmer" does not exact-string-match the rule config's condition value "Farmer", so RULE_24 silently fails to fire; (2) the Default-rule fallback path appears to incorrectly invoke RULE_26's Minor-only validation instead of correctly defaulting to Applicant Photo for a non-Joint, non-Minor customer. Designation/Profession was confirmed to have no effect on this routing (ruled out as a cause). | URL: https://sahyogagentweb.drutam.in:9634/applndetails ¦ Application: SAH-1002-775 (Individual, Shubham Vasant Zambre, mobile 9049971144, DOB 1995-09-21) ¦ Employment Type values tested: Agriculture/Farmer, Unemployed, Other, Business ¦ Funding Mode: both Cash and Cheque ¦ Browser: Chromium (headed) ¦ Env: UAT | New | STR: 1) Open a real Individual application at the Basic Details step with a valid adult DOB already saved 2) Fill all other mandatory fields 3) Set Employment Type to Agriculture/Farmer (or Other, or Business) and Funding Mode to Cash or Cheque 4) Click Submit 5) Observe inline error "Employment type is invalid for Minor." instead of advancing to Self Employed Information (Farmer) or Applicant Photo (Other/Business) per aoscust_module_rules_setting.xlsx | High | Major | Functional | Not Retested |  |  |  | Found during live branching-matrix exploration of the Funding Mode / Employment Type navigation logic (AC27 in US_008). Reconciled directly against the routing config document aoscust_module_rules_setting.xlsx supplied by the team — the mismatch between actual and configured behavior is unambiguous, not a business-rule interpretation question. Blocks real adult Individual customers from ever completing the application with these Employment Types; no workaround exists. See US_008 AC27 for full root-cause analysis and the reconciled flow matrix.
BUG-SILVER-006 | 10-Aug-2026 | UAT | Silver Savings Account — Nominee Details (management table) | Nominee table's Action-column "Submit" button produces no observable effect when clicked | On the Nominee Details step (a management table with columns Full Name / Status / Delete / Action, same pattern as Joint Applicant Details), the Action column contains a visible, enabled button labeled "Submit" intended to resume a Pending nominee's own sub-stepper (its Full Name/Relation/DOB form, then its nested Registered Address sub-step). Clicking this button — verified via three different strategies (a normal Playwright locator click, a forced click bypassing actionability checks, and a precise mouse click at the button's exact bounding-box coordinates) — produces no observable effect whatsoever: no page navigation, no toast/success message, no validation/error message, and the panel content is byte-for-byte identical before and after the click. A working alternative was found: clicking directly on the row's Full Name text (e.g. "Madhukar Pandurang Zambre") correctly reopens the nominee's own form with previously-entered values intact (the Relation dropdown value persists; other fields round-trip correctly on resubmission), and the flow can be continued normally from there. | URL: https://sahyogagentweb.drutam.in:9634/applndetails ¦ Application: SAH-1002-775 (Individual, Shubham Vasant Zambre) ¦ Nominee: Madhukar Pandurang Zambre, Relation: Father ¦ Browser: Chromium (headed) ¦ Env: UAT | New | STR: 1) Reach the Nominee Details step with at least one nominee already added and status "Pending" (not yet fully completed through its own Address sub-step) 2) Navigate away (e.g. reload, or leave and return to the application) so the Nominee Details tab renders as the management table 3) Click the "Submit" button in that nominee row's Action column 4) Observe no navigation, no toast, and no error — the button appears to do nothing. Workaround: click the row's Full Name text instead, which correctly resumes the sub-stepper. | Low | Minor | UI | Not Retested |  |  |  | Found during live exploration of the Individual Account Type full journey (AC28 in US_008), needed to resume an in-progress nominee after the table view reset on re-entry (matches the app's general "resets to initial state on tab re-entry, data persists server-side" pattern documented elsewhere, e.g. BR9). Low priority since a working alternative exists, but a dead "Submit" button is a real UX defect worth fixing — likely the button's onClick handler is missing or wired to a no-op, while the row's own onClick (bound to the Full Name cell or row) is the actual working resume mechanism.
BUG-SILVER-007 | 10-Aug-2026 | UAT | Silver Savings Account — Guardian Details (Minor Account Type) | Deleting an existing Guardian Details record fails with a generic "Oops something went wrong" error | On the Guardian Details management table (Minor Account Type applications), clicking the Delete icon on an existing guardian row shows a confirmation dialog ("Are you sure you want to delete this Guardian Details? No/Yes"). Confirming with "Yes" fails with a generic "Oops something went wrong" error, and the guardian record is NOT actually removed — confirmed via a fresh page reload showing the same guardian record still present and unchanged. This blocks any workflow that requires removing or replacing a guardian record, e.g. entering a different mobile number once the field becomes locked/disabled after first use. | URL: https://sahyogagentweb.drutam.in:9634/applndetails ¦ Application: SAH-1002-355 (Minor, Bhushan Vishnu More) ¦ Guardian: Shivshankar Prakash Vyavhare, Customer ID 400172191 ¦ Browser: Chromium (headed) ¦ Env: UAT | New | STR: 1) Open a Minor application at Guardian Details with an existing guardian record 2) Click the Delete (trash) icon in that row 3) Confirm "Yes" on the "Are you sure?" dialog 4) Observe "Oops something went wrong" error 5) Reload the application and confirm the guardian record is still present, unchanged | Medium | Major | Functional | Not Retested |  |  |  | Found while investigating how to change a guardian's already-locked mobile number, since the field becomes disabled after first entry. Both Delete (this defect) and re-Add (BUG-SILVER-008) being broken meant a fresh application had to be started instead. See US_008 AC29 for full context.
BUG-SILVER-008 | 10-Aug-2026 | UAT | Silver Savings Account — Guardian Details (Minor Account Type) | "+ Add" button remains enabled on Guardian Details even when the 1-record maximum is already reached | The Guardian Details management table's "+ Add" button (intended to add a new guardian record) remains visible and enabled even when a guardian record already exists and only 1 is allowed per application. Clicking it surfaces the message "Only 1 record allowed" instead of the button being disabled or hidden once the limit is reached, misleadingly inviting an action the backend will always reject. | URL: https://sahyogagentweb.drutam.in:9634/applndetails ¦ Application: SAH-1002-355 (Minor, Bhushan Vishnu More) ¦ Browser: Chromium (headed) ¦ Env: UAT | New | STR: 1) Open a Minor application at Guardian Details with 1 existing guardian record 2) Click "+ Add" 3) Observe "Only 1 record allowed" message instead of the button being pre-emptively disabled/hidden | Low | Minor | UI | Not Retested |  |  |  | Same root scenario as BUG-SILVER-007 — needed a way to add a second/replacement guardian and neither Delete nor +Add allowed it. Low priority UX polish item: disable/hide "+ Add" once the record-count limit is reached, consistent with how other 1-item-max UI elsewhere in the app behaves.
BUG-SILVER-009 | 11-Aug-2026 | UAT | Silver Savings Account — Branch Selection | "Change Branch" selection does not persist unless the outer step's own Submit is clicked in the same session | On Branch Selection, using "Change Branch?" to search for and select a different branch (confirmed working: search filters correctly, selection updates the visible summary card to the newly-chosen branch) does NOT actually persist server-side by itself. If the application is reopened in a fresh session before the Branch Selection step's own Submit button is clicked, the branch silently reverts to the original default with no warning message — confirmed on a real application whose final Summary page showed the default branch (AMGAON BRANCH) rather than the branch that had been deliberately changed to (GOREGAON BRANCH) earlier in the same journey. | URL: https://sahyogagentweb.drutam.in:9634/applndetails ¦ Application: SAH-1002-804 (Minor, Bhushan Vishnu More) ¦ Default branch: AMGAON BRANCH (1005) ¦ Attempted change: GOREGAON BRANCH (1002) ¦ Browser: Chromium (headed) ¦ Env: UAT | New | STR: 1) On Branch Selection, click "Change Branch?" 2) Search for and select a different branch, confirm the summary view updates to show it 3) Close the browser / open the application fresh in a new session WITHOUT clicking the outer Submit button first 4) Re-open Branch Selection and observe it has reverted to the original default branch 5) Confirmed via the application's final Summary page still showing the original default branch | Medium | Major | Functional | Not Retested |  |  |  | Found while deliberately testing "Change Branch" live for the first time in this project (previously only documented from the original story text, never executed). A real user completing a multi-day/multi-session application could easily lose an intentional branch change without any indication. See US_008 AC29 for full context.
BUG-SILVER-010 | 11-Aug-2026 | UAT | Silver Savings Account — Liveliness Verification (nested/Guardian sub-flow) | Camera-based Liveliness Verification fails to save after video capture completes, for a nested applicant (Guardian) sub-flow | For a Guardian's own Liveliness Verification sub-step (Minor Account Type applications), the camera-based Liveliness option was completed on the customer's real device: the video was recorded and the page appeared to proceed through a loading state as if successful, but then failed with "Failed — Saving application details are not present! Please contact to your advisor!" (confirmed via a real screenshot from the device). A backend status check immediately after confirmed the Liveliness step remained "Pending" — the result was never actually saved despite the apparent frontend progress. The issue reproduced across 2 real attempts (an initial send and one resend); all resend attempts were then exhausted ("Link attempt exceeded. You are blocked for 1 hr"). Switching to the alternative Security Code Based Liveliness method succeeded without issue, allowing the journey to continue, but camera-based Liveliness is currently a dead end for at least nested/non-primary applicants. | URL: link sent to guardian mobile 9511996248 ¦ Application: SAH-1002-804 (Minor, Bhushan Vishnu More) ¦ Guardian: Pagar Jayesh Arun ¦ Browser: real Android device (Chrome mobile) for the link; Chromium (headed) for the agent-side app ¦ Env: UAT | New | STR (device side): 1) Open the Liveliness verification link sent to the applicant/guardian's real phone 2) Follow the on-screen instructions to record the liveliness video 3) Observe the page proceeds to a loading state as if the video was accepted 4) Observe the page then shows "Failed — Saving application details are not present! Please contact to your advisor!" ¦ STR (agent side): 5) Re-check the Liveliness Verification status on the application — confirm it remains "Pending" despite the customer having completed the capture flow. Screenshot of the real device failure captured and reviewed. | High | Major | Functional | Not Retested |  |  |  | Discovered while completing the Guardian's own sub-journey for the AC29 Minor Account Type exploration. Not yet confirmed whether this is specific to nested/non-primary applicants (Guardian/Joint Applicant sub-flows) or also affects the primary applicant's own camera-based Liveliness — the primary applicant's camera-based Liveliness succeeded without issue earlier in this project (AC15, TC-SIL-054), so this may be specific to the nested-applicant code path. Worth a targeted retest on a Joint Applicant's own Liveliness step to determine scope. See US_008 AC29 for full context.
BUG-SILVER-011 | 11-Aug-2026 | UAT | Silver Savings Account — Guardian Details (Minor Account Type) | Guardian Details page-level Submit shows misleading "Cannot submit minimum 1 record required" error if the row-level Submit isn't clicked first | On Guardian Details, once a guardian's own sub-journey is fully complete (every inner step showing "submitted successfully"), clicking the step's page-level (bottom) Submit button directly produces the error "Cannot submit minimum 1 record required." — despite exactly 1 fully-complete guardian record genuinely existing in the table. The actual required sequence is: (1) click the row's own Action-column "Submit" button first, which correctly changes the row's Status from "Pending" to "Successful", and only then (2) click the page-level Submit, which correctly advances the journey to the next stage. The error message is misleading — it implies no records exist at all, when the real issue is that the existing record has not yet been individually confirmed via its own row-level action. | URL: https://sahyogagentweb.drutam.in:9634/applndetails ¦ Application: SAH-1002-804 (Minor, Bhushan Vishnu More) ¦ Guardian: Pagar Jayesh Arun, fully complete (eKYC Successful, Liveliness Successful, Address/Basic Details/Salaried Information/Applicant Photo all saved) ¦ Browser: Chromium (headed) ¦ Env: UAT | New | STR: 1) Complete every inner sub-step of a Guardian's own sub-journey (Mobile OTP, eKYC, Liveliness, Address, Basic Details, Salaried Information, Applicant Photo) 2) Without clicking the row's own Action-column Submit, click the page-level (bottom) Submit button directly 3) Observe "Cannot submit minimum 1 record required." despite the 1 existing record being fully complete 4) Instead click the row's Action-column Submit — Status correctly changes to "Successful" 5) Now click the page-level Submit — it correctly advances the journey | Medium | Minor | Validation | Not Retested |  |  |  | Discovered while finalizing the Guardian Details step during the AC29 Minor Account Type exploration; this confusing error initially looked like a hard blocker until the correct row-Submit-first sequence was identified. Recommend correcting the error message to something like "Please confirm the existing record(s) before continuing" to avoid misleading users into thinking a record is missing. See US_008 AC29 for full context.