## Defects
Defect ID | Date | Instance | Module | Title | Description | Test Data / Required Info | Status | Screenshot / STR | Priority | Severity | Type | Retested Result | Developer Assigned | Resolved Date | Developer Comment | QA Comment | Changes Applied
DEF-002 | 30-Jul-2026 | QA | Account Activation | Reloading /activeteUser redirects to Login instead of preserving the activation flow | A hard reload of /activeteUser drops the client-side route entirely and lands on /login, losing the user's place in the activation flow — the same defect class as Forgot User ID's reload behavior (unlike /login, the SPA fallback route, which trivially survives a reload). | Chrome (Desktop); URL: /activeteUser; Action: browser reload | New | Automated: TC-AA-011 in tests/AA_TS001/account-activation.spec.ts | Low | Minor | Functional | Not Retested |  |  |  | Confirmed via automated TC-AA-011, reproduces consistently.
DEF-003 | 30-Jul-2026 | QA | Account Activation | Submit button not disabled during in-flight activation request | A rapid double-click on Submit fires two identical otp/request calls instead of the second click being blocked, i.e. the button is never disabled while the activation request is in flight. | Chrome (Desktop); URL: /activeteUser; Action: rapid double-click Submit with valid-format data | New | Automated: TC-AA-015 in tests/AA_TS001/account-activation.spec.ts | Medium | Major | Functional | Not Retested |  |  |  | Confirmed via automated TC-AA-015, reproduces consistently.